## Slide 1: Systemic Risk Management for Projects
Bob Ferguson

## Slide 2: Theme
Using a systematic approach to risk management quickly provides improved visibility into projects.
Improved visibility provides better project change control and more predictable results.

## Slide 3: Agenda
Risk Management History at CommWorks
The Risk Management Metric
  Assessing Impact
Basic Risk Management Process
Documenting a Risk
Strategies for Managing
Making it work!

## Slide 4: History @ CommWorks
Risk Identification was required in project plans.
  One time event, then loosely tracked.
  No formal training.
  Very simple tool.
  Usually only R&D risks tracked.
We need a motivator to get better!

## Slide 5: 3Com Corporate Decree
CommWorks response was to develop a project dashboard.
“80% of R&D Projects must deliver within 10% of scheduled time.”

## Slide 6: The Project Dashboard
EXISTING DATABASES
QUERY & FORMAT
EMT / BMT METRICS & REPORTS
CONSOLIDATE
DIGITAL DASHBOARD
 HOW MUCH (SIZE)
 HOW GOOD (QUALITY)
 HOW FAST (SCHEDULE)
 RESOURCES (STAFF)
 REQUIREMENTS STABILITY
 RISK
6 CHARTS
Notes: The dashboard is based on some simple principles. Resources and requirements drive the project. You should see progress by looking at size, quality and schedule metrics. You can judge uncertainty from risk.

## Slide 7: Deriving a System Risk Metric
Risk = probability * impact
How do we measure impact and probability when both of these carry so much uncertainty?
Use big uncertainty buckets.
Use a likelihood type estimator for total risk by totaling individual risks.
Notes: Statistical theory will explain likelihood estimators.

## Slide 8: Probability: Big Uncertainty Bucket 1
Pick a range; use the midpoint for metric.
  Rare: 0-10%
  Unlikely: 10-30%
  Common: 30-70%
  Frequent: 70-90%
  Certain: 90-100%
Rare = you’ll see it one time in your career.
Certain = you’ve never seen it fail to happen.
Notes: Rare is 5%. This means, if you look at 20 projects, this risk will materialize once. In your career at a company, you will probably manage between 2 and 10 projects, so you should never see it.

## Slide 9: Impact: Big Uncertainty Bucket 2
Psychology: projects get cancelled when
  No customers
  100% schedule overrun
  100% cost overrun
Therefore that’s highest level impact=5
Psychology: people will estimate within a factor of 2,
Therefore buckets differ by a factor of 3.
Notes: I one time had someone ask why we would do a project with no customers. Of course the answer is that you never plan to do a project that has no customers. However, I have seen many projects delivered or near delivery, that had no customers. They never started that way, but it has always been easy to cite the examples wherever I have been employed.

## Slide 10: No Customers???!!! -- An aside.
Customer’s business can change.
Misjudge the market readiness.
  Too early or too late to market.
Competitor has better feature mix.
  Non-functional goals missed.
  Usability, manageability, performance, availability…
Risk is greater with few customers.

## Slide 11: Impact numbers example
Project
  Schedule: 18 months
  Cost $9 million
  Customer first year revenue = $36 million
Impact using factor of 3 scale.
  5 = 18 months, or $9M cost, or $36M revenue
  4 = 6 months, or $3M, or $12M
  3 = 2 months, or $1M, or $4M
  2 = 3 weeks, or $300K or $1M
  1 = 1 week, or $100K, or $300K

## Slide 12: Impact Use
Impact =1
  Team or component lead usually has contingency to handle a few of these incidents.
Impact =2
  Team or component lead has contingency to handle at most one of these incidents.
Impact >= 3
  Requires senior management attention when it occurs.

## Slide 13: Risk Metric
Single Risk = Probability * 3 ^ (Impact-1)
Sum top 20 risks for Project Dashboard
  (statistical likelihood estimator)
Set threshold at 81.
  Project cancellation level initially = Impact = 5
  So Cancellation = 3*3*3*3 = 81
Expect risk profile to decrease toward end of project.
Expect risk profile to increase at start.
Check it every week.

## Slide 14: Risk Management as a Process
Notes: Following slides detail the activities in each stage.

## Slide 15: Identify
Solicit input. Stage the event.
Source, Risk events (scenario), Risk symptoms
How would the impact of this risk event affect other processes and activities?

## Slide 16: SEI’s Taxonomy for Risks
Notes: The idea is to create some set of classifications that help to understand the impact and possible mitigation or avoidance strategies. Also it may help to understand that some uncertainties have to be accepted.

## Slide 17: Risk Sources
Product Engineering
  Requirements & Specifications
    Completeness, clarity
    Stability and scale
  Design and quality goals
    Measurable and achievable
Notes: Risks may be that PLM did not talk to the “right customers” so that requirements are incomplete. External standard may not be stable. Customer cannot make quality goals measurable (Performance > 1,000 calls per hour.)

## Slide 18: Risk Sources
Development Environment
  Work Environment
    Completeness, clarity
    Stability and scale
  Design and quality goals
    Measurable and achievable

## Slide 19: Risk Sources
Program Constraints
  External events, milestones
    CommNet, …
  Resources
    Hiring, lab space,
  Budget
    Prototypes, travel, missed estimates, …

## Slide 20: Plan: Strategies
Mitigate or Avoid:
  Spend resources early to avoid the scenario or reduce the impact.
Transfer:
  Hire 3rd party to take this risk. At the same time, add the new risks associated to using 3rd party.
Contingency:
  Set aside some resources to deal with this set of risks. Possibly develop work plan.
Ignore:
  Deal with it when it comes.

## Slide 21: Special Note
If you have spent money to mitigate, avoid or transfer a risk, Either
  Modify the probability or impact, or
  Close the risk, or
  Create a new one to represent the new situation.

## Slide 22: Track
Status
  Report on top 20
  Review scenarios to see if risk can be closed or other adjustment can be effected.
Forecast
  See if near-term, mid-term, long-term exposure can be adjusted.

## Slide 23: Control
Priorities
Assign
Exercise contingency
Escalate
  Risk becomes an issue or change request.
Close

## Slide 24: Documenting a Risk
Who
  Anyone should be allowed to identify a risk.
Write Scenario Description (or context)
  Describe the event or situation that poses the risk.
  Describe a likely timeframe in which it could occur.
  Describe probable symptoms of occurrence.
Describe Consequences
  Describe the potential impact in terms of delay, extra resource cost, other cost, diminished quality or product will miss target market.

## Slide 25: Analyze
Probability
  Evaluate probability (Rare-Certain)
Impact costs
  Allow only one major impact per risk: either schedule, cost or revenue.
  If another impact has equal importance, document another scenario.
  This will focus any mitigation, avoidance or contingency strategy on the most important resolution.
Assign Impact Rating: 1-5

## Slide 26: Risk Analysis Basic Steps
What is the likelihood of the scenario?
What is the impact?
  What type?
  How much?
  Keep it simple. Don’t out-think yourself.
Is this one important enough to bother me?
  The “risk exposure” places it on my Radar Screen.

## Slide 27: Risk Analysis: Impact Assessment:
Delay
  The schedule will slip for the associated activities.
  Some rescheduling and reassignment will be required to adjust.
  If the slip causes the critical path to exceed the contingency, then senior management must be notified.
  If the reassignment costs too many resources then senior management must be notified.

## Slide 28: Risk Analysis: Impact Assessment
Risk types that cause delays
  Suppliers
  Configuration management problems
  Design flaws particularly integration problems
  New technology application
  Team and people problems

## Slide 29: Risk Analysis: Impact Assessment:
Cost
  Resources or dollars required to complete the work are greater than planned.
  Rescheduling may allow project to operate at a lower on-going cost.
  Some types of rework.
  External costs typically must be reported immediately.
Notes: Ask for examples. Forgotten features. Test equipment requires outside lab. Have to repeat an outside test (UL, etc.).

## Slide 30: Risk Analysis: Impact Assessment:
Risk types that increase cost
  Customer product requirements are greater than anticipated.
  Customer support requirements are greater.
  Meeting customer quality goals increases design cost.
  Team is not sufficiently skilled to do the work as planned so more people are needed.
  External e.g. prototype, consulting, other contract etc., costs were underestimated.
  Rework for outside testing, prototype, etc.

## Slide 31: Risk Analysis: Impact Assessment:
Miss the revenue target
  The product as delivered fails to meet certain customer criteria.
  The customer refuses to pay for the product or negotiates reduced payment.
  The number of customers is reduced.

## Slide 32: Risk Analysis: Impact Assessment
Risks that cause target misses.
  Customer requirements were not clear.
  Customer operating environment changes mid-project.
  Customer business strategy changes.
  Too few customers at project initiation.
  Design is too hard to use.
  Attempt to deliver technology too early for market.
  Design is too late for market.
Notes: Offer examples. Mediaways did not take the Universal Port software. We have no sales for UC 6.2.

## Slide 33: Response Development Goals
Reduce likelihood of occurrence.
Reduce magnitude of loss.
Change the timing of the risk.
  How does changing the timing help?

## Slide 34: Response Development Principles
Deal with important risks first
Do we know enough about this risk?
Can we live with it?
Can we take action now? When?
Should we cancel the project or change the scope?
Balance the risk with the cost to do something about it.

## Slide 35: Possible Responses
Ignore it
Keep it as a risk (contingency)
Avoid it (do things differently at a cost)
Mitigate (reduce the potential impact at a cost)
Transfer (give it to someone else)
    Usually means accepting a different risk too!

## Slide 36: Response: Ignore It
Typically because the risk has impact 1 or 2 and lower probability.
  Unlikely * 2 impact = (20%*3 = .6).
  Even summing two or three of these is manageable at the team or component level.
Largest impacts=5 cannot safely be ignored regardless of probability.
  Rare * 5 impact = (5% * 81) = is 4% of budget
  This places it in top 20 risks automatically.

## Slide 37: Response: Contingency
Some budget (resources, schedule, costs) that you have not explicitly allocated.
  Allocation will occur as needed.
  Minimum range is 10%
  This is equivalent to the realization of one Impact-2 risk or several Impact-1 risks.
Contingency plans are a good example of how risk management can help project planning.
  Discuss Impact ≥ 3 contingency plan with Management

## Slide 38: Using Contingency
Communicate usage with status report
    “Tasks x, y slipped 3 days. No schedule adjustment is needed yet.”
Warn when contingency will be exceeded
    “Task z will slip 5 days. Since we have already slipped 3 days, this affects critical path next week, and we will have to re-schedule.”
Re-plan when contingency is exhausted

## Slide 39: Response Development: Avoidance
Use when the exposure is high and there is an alternative way of doing the work.
  Examples
    Hire a consultant to work with the team to improve skills.
    Use a proven technology instead of new.
    Prototype early use of new technology.
Implies additional cost or schedule, or reduced function or quality.

## Slide 40: Response Development: Mitigation
Protect function and quality at modest additional time/cost.
  Examples
    Two parallel development teams
    Extra testing
    2nd prototype using different technology
Protect schedule at modest cost.
    Develop simultaneously on old and parallel new technology

## Slide 41: Response Development: Transfer
Use when risk is based on factors in the development environment.
  E.g. skills, environment, process, technology
  Examples: protocol stack, specialized testing, optical components
Always introduces additional risks associated with external constraints.

## Slide 42: Response Control Process Objectives
Provide visibility into risk status.
  Monitor the events and conditions of risk scenarios.
  Track risk indicators for early warning.
  Provide notification for triggers.
The planned response brings project back into control!

## Slide 43: Risk Indicators: How can you tell?
Periodic reporting: what to watch
  Regular metrics and reports keep risk events under watch. (e.g. OTD charts)
  Look to action item list, work not completed. (list is growing too fast)
  Read individual status reports for risk events.
Notes: Warrants some discussion. An action item or issue count that shows the number is growing for 4 weeks could be a good indicator of a problem. OTD schedule chart is a good indicator. Resource status is a good indicator.

## Slide 44: Response Control: visibility
How frequently should we track?
  Team: weekly
  Program management: weekly, monthly
Keep notes to show whether likelihood is increasing or decreasing.
The scenario is past. Close it!
It happened. Implement contingency!

## Slide 45: Response Control: change
Re-balance resources
  Overtime, borrow people
Re-schedule
  Take no small slips. Make sure that the new schedule is achievable.
Re-scope
  Delete functionality, demonstrations & trials

## Slide 46: Making it Work
Tool Development
Visibility
Training

## Slide 47: Tool Development
Copied a freebie called Risk Radar.
Made it an MS SQL database application.
  Added some process elements including metric.
  Web entry
  Reports in Word and Excel by component or system
Metric implemented for component and system level projects.
  Means we know the relationship of component and system.

## Slide 48: Tool Use
Anyone can submit a risk.
Program managers have control over state.
  New
  Track
  Close

## Slide 49: Making it work
Using the metric
  Report to project team on a weekly basis.
  Invite team to do further investigation if risk is low.
  Show chart to senior management if risk is high.
  Explain to senior management how risk chart is data they can use.
    Influence sales, marketing, budgets, etc.

## Slide 50: Reporting and Management
Engineering Management Team (EMT)
  Overall risk profile (chart)
  New risks
  High impact risk problems
  Near term actions move to action item list
Past Term
  Review for closure
  Report “Retired” risks.
Total EMT time 6-10 minutes?

## Slide 51: Reports
Senior Management
  Scorecard available weekly.
  Senior management understands threshold.
OTD Chart
  Includes any “Accepted” risk, not Retired.
  Does not include “New” risks.
  Top 20 list calculated automatically

## Slide 52: Training!
Audiences
  Program managers– Detailed half-day session.
  Senior managers – Like this presentation
Identification
  Finding the risks: Taxonomy
  Documenting takes practice sessions.
Analyzing
  Assessing risk
  Response Strategies
  Response Development

## Slide 53: Training!
Response Control
  Contingency & Escalation
Risk – Issue – Change Request?
  Managers have to assess which way to manage.
  Issue implies some work has stopped, or will immediately.
  Change request means something was thought to be complete, and requires rework.
  Risk is forward looking and uncertain.

## Slide 54: Links & References
SEI
  Continuous Risk Management Guidebook, Aug 1998
  http://www.sei.cmu.edu/programs/sepm/risk/
Risk Radar: Software Program Managers’ Network
  http://www.spmn.com/rsktrkr.html
Robert N Charette-- RiskTrak
  RiskTrak training software on CD
  http://www.risktrak.com/rst/Products/charette.htm
  RiskTrak product ordering
  http://www.risktrak.com/index.html